Juniata College Center for International Education

Procedures Checklist

Eagles Abroad Short-Term Program Development

Because of budgetary and legal implications, the Provost has determined that faculty members who wish to develop programs abroad must follow these procedures established by the Center for International Education (CIE).

BEFORE THE PROGRAM

As soon as you have an idea for a program

___ Meet with CIE staff to discuss process.

16 months before departure

___If you are requesting development funds, submit a Faculty Statement of Interest with a program development budget request to the CIE

___ Attend CIE short-term program development workshop

12 months before departure

___ Submit a completed Faculty Statement of Interest to the CIE.

___  Conduct a program development trip/determine program travel and lodging logistics.

6-8 months before departure

___Submit Faculty Proposal including Program Budget

___ Obtain program and course approval from academic administration

___ Design program flyer/ webpage and other promotional material including the application deadline

(4-6 months prior to program), deposit deadline (3-4 months prior to program), credits, type of credits, and program dates and fees (what is/ is not included)

___ Create application including housing preferences, insurance information, etc.

___ Recruit students (and attend study abroad fair to market the program)

___ Attend CIE safety and liability workshop

4-6 months before departure

___ Provide list of interested applicants to CIE

___ Students are to complete Eagles Abroad application form, including statement of interest, recommendations, etc., in CIE

___ Determine application deadline; establish by when student enrollment makes program feasible

___ Send conditional acceptance letters; have students obtain passports (and begin visa process, if necessary); indicate that travel is contingent upon clearance by campus offices

___ Begin process for airline ticket details (might need passport numbers, DOB info on each traveler; will everyone fly together, or from separate airports, where will you meet up in that case?), special travel permission, etc.

___ Begin process for visa, if necessary

3-4 months before departure

___ Collect program deposits or fees; confirm airline tickets

___ Remind students to attend CIE General Pre-Departure Orientation (October and March)

___ Conduct program-specific pre-departure orientation sessions -- include student conduct, expectations and responsibilities; local customs; safety concerns; culture and culture shock; information students can give to parents including expenses and contact details

___ Research obtaining an international cell phone

___ Prepare a file of emergency contact information, student contact and health forms, travel advisories from US government

4 weeks before departure

___ Obtain ISIC card for each participant and self

___ Obtain copies of passports, health form, and emergency information from all participants

___ Make sure students are cleared to study abroad with campus offices (Accounting, Dean of Students, Student Wellness)

1 week before departure

___ Establish with accounting that all student program payments have been made

___ Have students sign release forms, statements of understanding, behavioral contracts where necessary

__ Discuss how participants will communicate with parents to announce safe arrival

__ Submit off-campus safety form to Juniata (web)

DURING THE PROGRAM

__ Notify CIE of safe arrival

__ Identify emergency location and telephone numbers (police, hospitals)

__ Keep detailed budget information including receipts, where possible

__ Identify any new and useful contacts made at site for future possibilities

__ Report and document any complaints or incidents involving participants

Towards end of program

___ Give students evaluation forms and collect them on last day

AFTER THE PROGRAM

__ Conduct post-program reintegration event(s)

__ Complete a program leader evaluation, including photos

__ Clear budget

__ Submit student grades to Registrar